|  | ACTIVITY REPORT of OEAW | Report period 09/2006–11/2006 |
| --- | --- | --- |
| WP nr & name WP1-7 | Task nr. & name (according to the “Description of Work”) |
| Work accomplished / results New employees: Sep. 2006: Dr. Vlad ATANASIU (VISKOM, ÖAW) Oct. 2006: Mag. Martin HALTRICH (KSBM, ÖAW) Sep. 2006: Mag. Sandra HODEČEK (VISKOM, ÖAW) Management: organization of the kick-off meeting organization of several workpackage meetings (integration, expertise) coordination with partners and PO administration of the TWiki and project website preparation of use cases completed the “graphical image” presentation document of the project (folder and poster) organization of the tutorial (local preparedness in Fabriano, schedule of tutoring personel, program) coordination of the imprint variability experiment coordination of the component model for database integration Software development: wrote wmscissors for segmenting pages from watermark repertories containing several watermarks into individual images of watermarks (see page ImageProcessing on the TWiki) wrote mark2file for obtaining coordinates lists of landmarks in watermarks (see page ImageProcessing on the TWiki) worked on new version of AD751 software for laid lines density measurements worked on automatic measurement of image features in hand drawn paper reproductions WZMA: preparation of WZMA-data for Leitner/Sinnerl working on a program for creating PDF-files where the images are connected to metadata converting wm-images to 100 dpi creating of new webpages: http://www.ksbm.oeaw.ac.at/wzrep/briquet.htm (therefore measurements for about 8000 images); http://www.ksbm.oeaw.ac.at/wz/lit/rep.htm Miscellaneous: preparation webpage for WIES (Watermarks of Spanish incunabula – Van Thienen) data preparation for Briquet webpage proof-reading of Piccard (Waage, Dreiberg, Werkzeuge u. Waffen) and Zonghi metadata general proof-reading (folder, poster, lectures, ...) |
| Dissemination activities (papers, talks, collaborations, advertisements…) DELIVERABLES Nov. 30th, 2006 - Deliverable 2, D6.2 Project presentation (multimedia PowerPoint presentation, poster, folder) Sept. 30th, 2006 - Deliverable 1, D6.2 Project website, TWiki (development site) LECTURES Nov. 9th, 2006 - EVA Berlin, lecture about Bernstein, Berlin Dec. 11th, 2006 - Wiener Archäographisches Forum (WAF), Generalversammlung, Akademie der Bildenden Künste, Vienna MEETINGS Dec., 14th-15th, 2006: Participation: WP2 Meeting, Stuttgart, Germany Oct. 10th, 2006 – Meeting at KSMB: Haidinger, Leitner, Sinnerl (database structure), Vienna, Austria Oct. 18th, 2006 - Meeting mit Kooperationspartnern der TU Graz, Meeting mit Interessenten der UB Graz, Graz, Austria Oct. 6th, 2006 - Meeting mit Interessenten der Akademie der Bildenden Künste und Kupferstichkabinett, Vienna, Austria Sept. 2006: Kick-off meeting, Paris, France PRESS Dec. 2006 – Press release (DIE PRESSE) Oct., 23rd, 2006 - Press release (APA) TUTORIALS, WORKSHOPS Tutorial at Cambridge University Library, 11. Dec. 2006 (methods of reproduction of paper structure) Nov. 27th-28th, 2006 - First EDLproject Workshop on developing the European Digital Library, Austrian National Library, Vienna MISCELLANEOUS Nov. 23rd, 2006 - Bernstein-Informationshalbtag (9-12 a.m.), Clubraum der ÖAW, Vienna Collaboration agreement with: Institute for Iranian Studies, Austrian Academy of Sciences, on the study of the papers of an important medieval manuscript of the Austrian National Library Cambridge University, School of Oriental Studies, on support for setting up a database of papers from the Cambridge University Library National Library of Egypt, on support for setting up a database of papers from their medieval manuscripts |
| Materials bought / subcontracting (only in relation to this project) computer hard drive, RAM memory, USB memory stick, keyboard, graphic tablet. |
| Global evaluation in relation to the project’s objectives |
| Improvements proposals / Comments |