|  | ACTIVITY REPORT of KB | Report period 09/2006–01/2007 |
| --- | --- | --- |
| WP nr & name WP1 Integrated workspace WP4 Contextual resources for paper history | Task nr. & name (according to the “Description of Work”) T1.1: Integration model; T1.2: Workspace architecture & implementation T4.1: Paper-incunabula integration; T4.3: Historical cartography of paper |
| Work accomplished / results General: Participation in the Kick off Meeting (Paris, September 2006) and WP2 Meeting Stuttgart (14-15 December 2006). WP1, T1.1 & 1.2: Analysis and description of the database structure; researching possibilities to convert the MS Access structure to XML; gathering and providing information for the technical people of Bernstein; gathering and providing information for surface linking with Stuttgart and WMZA; investigation of the use of Briquet numbers for databasel linking. Result: technical documents about WILC; pilot webpage for possible integration model for the databases. WP4, T4.1: Visiting the British Library (December 2006) to deliberate about the manner and work to accomplish this; at the BL and Cheshire, Liverpool, the institution that does the technical maintenance of ISTC, work was timetabled for the last 3 weeks of January. The data that were needed from Munich has all been received, and is being tested. After that ILC numbers will be loaded and a link will be established between WILC. As regards the links, Cheshire will work on this in January, and will let know what implications there may be for WILC. WP4, T4.3: Exploring the possibilities of the CERL Geographical Thesaurus for Bernstein; deliberation with CERL; establish contact and exploration of possibilities between CERL and Bernstein Result: CERL people will meet Bernstein people in Vienna. |
| Dissemination activities (papers, talks, collaborations, advertisements…) |
| Materials bought / subcontracting (only in relation to this project) |
| Global evaluation in relation to the project’s objectives In this first stage all kinds of explorations and investigations have been done for WILC and integration. This work will be useful in the course of the project. |
| Improvements proposals / Comments … |